## Resource Fulfillment Board
Resource Fulfillment Analytics Agent — Team Sprint Board
Resource Fulfillment Analytics ¦ Internship Project ¦ June 2026
Ticket ID | Title | Assignee | Track | Description | Acceptance Criteria | Status
SAMARTH — DATA FOUNDATION · Kicks off first — everyone else depends on this layer
RF-01 | File Upload Experience | Samarth | Data Foundation | Build the upload screen with drag-and-drop, covering wrong file type, wrong sheet, missing columns, and empty file as distinct error states. | Accepts .xlsx/.csv via drag-and-drop or browse. Wrong file, missing columns, and empty file each show a specific error screen, not a generic failure. | To Do
RF-02 | Data Validation Engine | Samarth | Data Foundation | Validate uploaded rows for mandatory fields, duplicates, missing data, and invalid dates before processing begins. | Mandatory-field, duplicate, and invalid-date checks run on upload. Failed rows are available as a downloadable error report, not just a single summary message. | To Do
RF-03 | Data Mapping Engine | Samarth | Data Foundation | Map uploaded column headers to standard system fields, auto-resolving synonyms like "Skill," "Technology," and "Skill Name," with a manual mapping UI as fallback. | Common column synonyms auto-map correctly. Unmapped columns prompt a mapping UI. Mapping choices save as a reusable template for future uploads. | To Do
RF-04 | Skill Clustering Logic | Samarth | Data Foundation | Group raw skill text ("Java," "Core Java," "Java Developer") into the 9 defined skill clusters, with a clear rule for multi-skill entries like React/Node/Angular. | 95%+ of sample skills cluster correctly against the validated mapping. Unmapped skills are flagged for review, never silently dropped. Cluster mapping is stored and reused across uploads. | To Do
RF-05 | Skill Standardization & Lead-Time Engine | Samarth | Data Foundation | Standardize inconsistent skill spellings via fuzzy matching and calculate the lead-time formula (Fulfilled Date − Raised Date) that every downstream metric depends on. | Duplicate skill spellings collapse to one canonical name. Lead time is calculated correctly for every valid row. Output matches the transformed structure in the training guide. | To Do
GAURAVI — ANALYTICS & METRICS · Turns Samarth's clean data into the numbers leadership sees
RF-06 | Internal vs External Analysis | Gauravi | Analytics & Metrics | Calculate internal/external fulfillment volumes and percentages, and define the single metric that best signals overdependence on external hiring. | Internal % and external % calculated per cluster and overall. Comparison cards render with correct totals. Overdependence metric documented with its trigger threshold. | To Do
RF-07 | Fulfillment Health Score | Gauravi | Analytics & Metrics | Combine open positions, lead time, and internal/external ratio into one weighted health score, resolving whether 20 open positions or a 60-day lead time should weigh more. | Score formula and weightings documented. Score maps to clear categories (Healthy / At Risk / Critical). Tested against 3+ sample scenarios with expected results. | To Do
RF-08 | Lead Time Analytics | Gauravi | Analytics & Metrics | Calculate average lead times by skill cluster, location, and source type, and surface the clusters with the most significant delays. | Lead time averages calculated by skill, location, and source. Internal vs external view matches manual calculations. Slowest 3 clusters are clearly highlighted. | To Do
RF-09 | Demand Trend Analysis | Gauravi | Analytics & Metrics | Analyze fulfillment demand history to rank which skills are growing or shrinking, with a defined threshold for what counts as "trending." | Quarter-over-quarter growth calculated per cluster. Trending threshold is defined and documented. Top 3 trending skills rank correctly against sample data. | To Do
PRAGYA — BOTTLENECK & RECS · Explains why issues happen and what to do about them
RF-10 | Risk Identification Engine | Pragya | Bottleneck & Recs | Build rules to flag fulfillment bottlenecks with severity levels, covering the case where a low-demand skill is still high-risk. | Rules cover at least 3 bottleneck scenarios (high external %, long lead time, low volume + high specialization). Each risk carries a severity level. Low-demand skills can still be flagged risky when criteria are met. | To Do
RF-11 | Root Cause Analysis | Pragya | Bottleneck & Recs | Differentiate why a bottleneck is occurring — skill shortage, approval delay, or hiring delay — and generate a summary for each flagged risk. | Each flagged risk includes a labeled root cause. Logic correctly separates approval-stage delays from sourcing-stage delays using lead-time components. Summary insight text generates per root cause. | To Do
RF-12 | Recommendation Knowledge Base | Pragya | Bottleneck & Recs | Build the library of problem categories, recommendation templates, and rules, including tie-break logic for when multiple solutions apply to one problem. | Each problem category maps to at least one recommendation template. Tie-breaking logic is documented for multi-solution cases. Recommendations include investment and expected-impact fields. | To Do
RF-13 | Recommendation Generator | Pragya | Bottleneck & Recs | Generate recommendations dynamically based on severity, ranking actions so higher-severity problems surface stronger interventions. | Severity changes the suggested action (e.g., Critical → hire trainers now, Low → monitor only). Recommendations are ranked by ROI/feasibility. Cards render with priority, investment, and expected outcome. | To Do
ADITI — DASHBOARD & CHAT · Presentation layer — finishes last, consumes everyone else's output
RF-14 | Executive Overview Dashboard | Aditi | Dashboard & Chat | Build the leadership view with KPI, trend, risk, and recommendation widgets, designed to be understood in 15 seconds. | Exactly 5 headline KPIs shown above the fold. Dashboard renders in under 5 seconds. Each KPI card links to its drilldown. | To Do
RF-15 | Drilldown Experience | Aditi | Dashboard & Chat | Design the investigation path so a flagged risk (e.g., cloud skills) leads into skill-level and location-level detail, then into a recommendation. | Clicking a risky cluster opens detail with lead time, volume, and root cause. Location drilldown is available from the same view. Drilldown ends at a recommendation, not a dead end. | To Do
RF-16 | Manager Assistant Chatbot | Aditi | Dashboard & Chat | Build the natural-language chat interface so managers can ask questions like "why is DevOps external dependency high?" and get answers from the analytics engine. | Chatbot answers the top 20 manager question types identified during design. Responses return in under 3 seconds. Out-of-scope questions are handled gracefully, not as errors. | To Do
RF-17 | Insight Generation Agent | Aditi | Dashboard & Chat | Generate plain-language explanations — executive, recommendation, trend, and risk summaries — condensed to 3 sentences each. | Every insight type has a 3-sentence-max template. Generated insights reference actual underlying numbers, not generic text. Reviewed against sample data with zero hallucinated figures. | To Do